## Sheet1
January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Setup Github repo |  |  |  |  | Setup TwinCat for testing
| Explore Simscape | [6 empty] | More advaced simscape model with data from mapping
| Explore TwinCat 3 |  |  |  | Mapping valve and cylinder characteristics
Research and writing introduction | [6 empty] | Rapport writing
Simple crane simscape modell
Set up crane for cylinder force test
Category | Color name | HEX
PLC / Control | Light Green | #A5D6A7
Testing / Experiments | Light Blue | #90CAF9
Simulation | Light Orange | #FFCC80
Modeling / Development | Light Red | #EF9A9A
Writing / Documentation | Light Teal | #80CBC4
Analysis / Planning | Light Purple | #CE93D8